JISC DEVELOPMENT PROGRAMMES

Project Document Cover Sheet

PROGRESS REPORT

# Project

| Project Acronym |  | Project ID |  |
| --- | --- | --- | --- |
| Project Title | First World War Poetry Digital Archive |
| Start Date | April 2007 | End Date | March 2009 |
| Lead Institution | University of Oxford |
| Project Director | Dr Stuart Lee |
| Project Manager & contact details | Kate Lindsay English Faculty St. Cross Building, Manor Road Oxford OX1 3UQ Tel: +44(0)1865 271459 Email: katharine.lindsay@oucs.ox.ac.uk |
| Partner Institutions | N/A |
| Project Web URL | http://www.oucs.ox.ac.uk/ww1lit |
| Programme Name (and number) | Digitisation Programme |
| Programme Manager | Paola Marchionni |

# Document

| Document Title | Progress Report |
| --- | --- |
| Reporting Period | April – September 2007 |
| Author(s) & project role | Kate Lindsay, Project Manager |
| Date | October 2007 | Filename | WW1ProgressReportOct07 |
| URL | http://www.oucs.ox.ac.uk/ww1lit/about |
| Access | ( Project and JISC internal | ( General dissemination |

# Document History

| Version | Date | Comments |
| --- | --- | --- |
| v.1.0 | October 2007 |  |

# JISC Progress Report

## Overview of Project

### Grant Statement

The project is being conducted under the terms agreed with JISC in the letter of grant and the JISC Terms and Conditions attached to it.

### 2. Aims and Objectives

# No changes have been made to the aims and objectives stated in the project plan. These were:

# Aims

- To bring together and to make available highly valued primary source material that focuses on World War One poetry.

- Develop a web interface to enabling the searching, browsing, viewing and downloading of digitised items.  The interface will also allow the viewing and downloading of the text of war poems, biographical information of poets and contextual resources (images, audio, video) from the Imperial War Museum.

- The development of tools to allow users to create personalised paths through the archive and online tutorials for education will also be incorporated.

- To make material previously inaccessible to the scholarly community available through a “community collection”.  The general community will be able to submit their own digitised items to the archive via a web-based interface to be included in the final archive.

# Objectives

- The digitisation of approximately 2000 primary source items.

- Integration of machine-readable texts of poems.

- The development of a web based interface to search, browse, display and download items.

- The development of a web based interface to collect and catalogue items from the general public.

- The creation of metadata for each item.

- Implementation of path creation tool to allow users to create personalised paths through the archive.

# The early targets for this project extend this reporting period. However, to date (April – September 2007) the following targets are on schedule and near completion:

# Digitised images have been received for approximately 500 primary source items, with orders placed and work in motion for the remaining items.

# Metadata has been created for items received

- The technical architecture has been selected to search, browse, display, and download items.

# A web based interface to collect and catalogue items from the general public has been scoped and development is underway.

### 3. Overall Approach

The overall approach of overlapping flows of work remains the same, however a significant change has been that the project will now be using CONTENTdm as opposed to developing a bespoke content delivery system (see Section 9: Technical Development).

### 4. Project Outputs

No technical deliverables were scheduled in the original project plan for this period. A number of document deliverables have been met, these consist of:

- A detailed project plan (see: http://www.oucs.ox.ac.uk/ww1lit/documents/WW1ProjectPlan2007.pdf)

- Workpackage detail plans (see: Appendix B for edited workpackages)

- User requirements (See Appendix C)

- Technical specification (See Appendix C)

- QA and workflow plans (see Appendix D)

- License agreements

- Monthly project reports have been written and are available on the project blog at: http://ww1lit.blogspot.com/

### 5. Project Outcomes

It is too early in the project lifecycle to summarise achievement against objectives, however there is little to indicate that the project outcomes will not be met.

In terms of project development, there has been a lot of interest in the project from various groups, organisations and literary bodies. As a result the project has been contacted by the literary estates of a number of additional war poets and institutions that hold more contextual material to offer their items for inclusion in the archive. We are predicting an underspend in the digitisation budget due to changing costs since the submission of the original project proposal and a more selective identification of materials. This may facilitate the digitisation of some of these items, however it does not place us in a position to be able to digitize all materials. We intend to do some preliminary research on these potential collections and at the next steering group meeting we intend to put forwards the options for digitisation and let the committee guide us as to what should be our priority. The ability to select further items will change our timescale for digitisation and cataloguing  milestones, however we still intend to meet the original milestones for the collections originally identified in the project proposal. We also intend to seek further funding to enable us to digitise and catalogue more than our budget allows. In this respect, a lesson learned, has been that it is important to build contingency into the project plan for possible further work, which this project has done.

### 6. Stakeholder Analysis

One of the first activities that the project team did on start up was to brainstorm and identify the project stakeholders and possible routes for reaching those groups.

Project Stakeholders and Brokers

| Stakeholder | Broker |
| --- | --- |
| JISC | Programme Manager |
| Oxford University | Project Team |
| Literary Estates | Steering Group |
| Holding institutions | Contact at each institution |
| Researchers | The War Poets Association The Centre for First World War Studies at Birmingham University. Steering Group |
| Lecturers | Subject Centres |
| Students | Lecturers / teachers |
| School teachers | Subject Centres Departments of Education |
| General public (Military enthusiast, Genealogist, General Interest) | Western Front Association Imperial War Museum In Flanders Fields Museum The War Poets Association National Archives The Media (BBC, Newspapers ect.) Celebrities |

The projects steering group consists of individuals who are key in helping us to reach our stakeholders (see: http://www.oucs.ox.ac.uk/ww1lit/steeringgroup)

Engagement with stakeholders over the reporting period includes:

- Steering group meeting held in April 2007

- Presentations by the project team at Oxford University

- Various separate meetings with literary estates, subject experts and researchers.

- Contact made with Department of Education at Oxford and Birmingham University providing the project with a route for user testing, development of educational resources, feedback and dissemination within schools and adult education.

- Contact made with the Western Front Association, Imperial War Museum, In Flanders Fields Museum and the War Poets Association who have agreed to disseminate the archive, advertise the community collection and have invited the project to attend various events.

- Interviews with relevant public figures in the field (to date Ian Hislop, Max Arthur, Hew Stachen) released as podcasts on the project wesite and will be available on itunes.

- Organisation of workshop for 12th November on “Teaching First World War Literature” to include user testing and requirements gathering from lecturers and teachers and disseminate information on the archive.

- Representation at JISC events and workshops and meeting with programme manager

- Representation at the DRHA conference 2007

### 7. Risk Analysis

No problems have occurred in the reporting period.

### 8. Standards

There has been no change in the standards to be used in the reporting period.

### 9. Technical Development

Originally the project planned to develop a bespoke backend database and web based interface from scratch. The project has since decided to adopt a commercial open-source content delivery system (CONTENTdm) for this purpose. The system was rigorously tested against system requirements and met all of the project needs (see Appendix C).

### 10. Intellectual Property Rights

Usage contracts have been drawn up for all holding institutions and literary estates. Usage rights were agreed prior to the commencement of the project and the formalities of signing these agreements are underway.

## Project Resources

### 11. Project Partners

The majority of digitisation is taking place at the holding institutions. These consist of:

- The Imperial War Museum

- The National Library of Wales

- Cardiff University Library

- The British Library

- New York Public Library

- The Bodleian Library, Oxford

- The National Archives

- McMaster University

- The Poetry Collection, The University at Buffalo

In addition to the above we have secured rights with Proquest to use the full text versions of poems

Due to a unpredicted underspend for digitization,, additional literary estates and project partners have been sought to complement the collection. At the next steering group meeting we will reach a decision as to what additional items to digitise. This has no impact on the schedule for the digitisation of the items originally identified in the project plan, however it does mean that the process of digitisation will exceed it’s deadline of December 2007 to encompass the new material.

Possible additional project partners include:

- The Ivor Gurney Literary Estate

- The Siegfried Sassoon Literary Estate

- The David Jones Literary Estate

- The Edmund Blunden Literary Estate

### 12. Project Management

Because of the decision to adopt CONTENTdm agreed changes in the budget have been made in terms of staffing. As we will no longer require a dedicated full time developer money has been moved from this post into consultancy to outsource specific technical work packages. These include:

- Development of the community collection (Web Developer)

- Conversion of virtual seminars in the Wilfred Owen Multimedia Digital Archive (WOMDA) to compliment XHTML (Web Developer and Web  Designer)

- Development of the front end of the archive (Web developer and Web designer)

- Integration of the path creation scheme (Web developer)

- Development of educational resources and seminars (teachers and lecturers)

- Hosting and server maintenance (Network Solutions Maintenance Service, Oxford University)

Consultants to carry out the above workpackages have been sourced and contracted. They are:

Richard Doe, Web Developer

Richard Doe is an Internet developer focusing on web standards and open-source technologies. He studied Philosophy at Sussex University, and has worked extensively in the UK higher education and non-profit sectors. Richard produces accessible web applications with database back-ends, such as the Roman Provincial Coinage website

<http://rpc.ashmus.ox.ac.uk/> for the Ashmolean Museum. He has also provided development for the JISC funded Accessing and Storing Knowledge repository project (ASK). As the web developer for the First World War Poetry Digital Archive, he will be creating XHTML compliant content, building the community collection interfaces and database and also developing the core archive search and browse functionality.

Joseph Talbot, Web Designer

Joseph works as a Senior Project Officer with Academic Computing Development Team at Oxford University Computing Services, where he has worked since 2002 with a specialisim in graphic design and accessibility. He was previously a Web Developer for Technology-assisted Lifelong Learning (TALL) at the University of Oxford. Joseph has an MA in Electronic Media from Oxford Brookes University, for which he produced an online comic website - Oneironaut.net. Joseph will be creating the style sheets and graphical interface for the archive.

The technical specialist is primarily responsible for overseeing the work of the contractors.

This decision has had a positive impact upon the project timetable which in parts in now ahead of schedule.

### 13. Programme Support

Contact with the programme so far has been:

- Meeting with programme manger

- Attendance at JISC Digitisation conference

- Attendance Programme meeting

- Attendance at JISC Digitisation Conference Meeting

- Attendance at Project Management, Evaluation, Media and Metadata workshops

Further guidance on additional funding both for additional digitisation within the project timeframe and also for further work after its completion would be welcomed.

### 14. Budget

See Appendix A

The most significant change in the budget is that of the vi of funds from the web developers post into consultancy. The decision to use CONTENTdm and the contained, diverse, nature of the technical workpackages mean that using contractors and consultants and more efficient option than hiring one developer. This change has been approved by JISC and by Oxford’s Research Services.

\

## Detailed Project Planning

### 15. Workpackages

Because of the decision to use CONTENTdm, and also to select and digitise more material, some of the workpackages have been altered (see Appendix B for updated workpackages). Workpackages 1 and 2 have been completed, and the rest underway and on schedule.

The key objectives for the next reporting period are to receive and catalogue all digital images of primary and contextual items that were identified in the original project plan. To date about 500 items have been received and catalogued and the workflow is in motion for all the remaining items, which have been selected and ordered.

The next reporting period will also see the development and release of the community collection and the population of CONTENTdm with the digitised collections and corresponding metadata.

### 16. Evaluation Plan

Progress against plan for the reporting period

| Timing | Factor to Evaluate | Questions to Address | Method(s) | Measure of Success |
| --- | --- | --- | --- | --- |
| Ongoing | Creation of database | Does it have required functionality? Does it allow interoperability? Is it sustainable? | Review by project team Peer review | Design signed off. |
| Progress The Technical Specialist CONTENTdm’s functionality was mapped against system requirements (see Appendix C) and met all points. The technical solution was presented for peer review and was chosen as the archive’s delivery system. |
| Ongoing | Digitised images of primary documents | Image quality Delivery | Each image checked Delivery | 100% of images meet required quality. Images delivered on time and according to schedule. |
| Progress Image quality is checked during cataloguing and is built into the workflow (see Appendix D). So far 100% of images have met the required quality. To date all images have been delivered on time |
| Ongoing | Digitised audio | Sound quality Delivery | Each audio file checked Delivery | 100% of audio files meet required quality. Audio delivered on time and according to schedule. |
| Progress No audio files have yet been received |
| Ongoing | Digitised video | Picture and sound quality Delivery | Each video file checked Delivery | 100% of video files meet required quality. Audio delivered on time and according to schedule. |
| Progress No video files have yet been received |
| Ongoing | Integration of machine readable texts of poems | Poems from appropriate editions Delivery |  | Steering Group to sign off text. All documents delivered on schedule. |
| Progress Machine readable texts of poems are being identified from relevant editions with help from the steering committee. |
| Ongoing | Metadata | Appropriate content Content quality Delivery | Spot checks Steering committee | All metadata correct and delivered on schedule. |
| Progress So far all metadata has been QA’d and some adjustments made. |
| Ongoing | Documentation | Appropriate content Content quality Delivery | Peer review | Signed off and delivered on schedule. |
| Progress All documentation has been peer reviewed. |

No changes to the plan are needed and objectives for the following reporting period remain the same:

| Timing | Factor to Evaluate | Questions to Address | Method(s) | Measure of Success |
| --- | --- | --- | --- | --- |
| Ongoing | Creation of a web base interface to collect digitised items from the general public (community collection) | Interface design Site structure Site navigation Security Functionality Content delivery Usability Accessibility Performance Ease of Use Perceived Ease of Use | User evaluation Heuristic evaluation by experts Accessibility checks using software Load testing | Site meets all usability and accessibility benchmarks. |
| Ongoing | Creation of a web based user interface to allow searching, browsing, viewing, downloading of items | Interface design Site structure Site navigation Functionality Content delivery Usability Accessibility Performance Ease of Use Perceived Ease of Use | User evaluation Heuristic evaluation by experts Steering Committee Accessibility checks using software | Site meets all usability and accessibility benchmarks. |
| Ongoing | Implementation of path creation tool to allow users to create personalised paths through the archive | Interface design Site structure Site navigation Functionality Content delivery Usability Accessibility Performance Ease of Use Perceived Ease of Use | User evaluation Heuristic evaluation by experts Steering Committee Accessibility checks using software | Site meets all usability and accessibility benchmarks |
| Ongoing | Creation of new seminars | Appropriate content Content quality Delivery | User evaluation Peer review Delivery | All content correct and delivered on schedule. |
| Ongoing | Documentation | Appropriate content Content quality Delivery | Peer review | Signed off and delivered on schedule. |

### 17. Quality Assurance Plan

Progress against plan for the reporting period

| Output | A database which will deliver files to the web |
| --- | --- |
| Timing | Quality criteria | QA method(s) | Evidence of compliance | Quality responsibilities | Quality tools (if applicable) |
| April – May 07 | 1. Technical Standards 2. Interoperability Standards | 1. Checklist 2. Checklist | 1. Consistent with JISC guidelines. 2. Consistent with JISC guidelines. | TS |  |
| Progress A scoping study was conducted of various content delivery systems based on previous work conducted by Oxford University. CONTENTdm was chosen as the technical solution (see Appendix C). |

| Output | Digitised images of approximately 2000 primary documents. |
| --- | --- |
| Timing | Quality criteria | QA method(s) | Evidence of compliance | Quality responsibilities | Quality tools (if applicable) |
| April – December 07 | 1. Digitisation standards 2. Preservation standards - resolution - orientation - colour - crop | 1. Checklist 2. Checklist | All items checked plus subsequent check on all deliverables. Consistent with JISC and TASI guidelines. | PM, TS, C | QA checklist built into cataloguing software (Portfolio). |
| Progress QA of images has been built into the image workflow (see Appendix D). All QA of images so far has been successful with no errors reported. In terms of preservation standards – where possible all images have been scanned at 800dpi. However is some cases the holding institutions own digitisation guidelines have meant that images have only been scanned at 600dpi. The project feels this is acceptable for preservation in terms of quality. |

| Output | Digitised audio |
| --- | --- |
| Timing | Quality criteria | QA method(s) | Evidence of compliance | Quality responsibilities | Quality tools (if applicable) |
| April – December 07 | Digitisation standards - sample rate - bit rate - file format | Checklist | All items checked | TS | QA checklist built into cataloguing software (Portfolio). |
| Progress QA of audio will be built into the audio workflow, however no digitised audio has been received yet so this is yet to be implemented. |

| Output | Digitised video |
| --- | --- |
| Timing | Quality criteria | QA method(s) | Evidence of compliance | Quality responsibilities | Quality tools (if applicable) |
| April – December 07 | 1. Digitisation standards - bit depth - screen size - fames per second - file format | Checklist | All items checked | TS | QA checklist built into cataloguing software (Portfolio). |
| Progress QA of video will be built into the video workflow, however no digitised audio has been received yet so this is yet to be implemented. |

| Output | Creation of metadata |
| --- | --- |
| Timing | Quality criteria | QA method(s) | Evidence of compliance | Quality responsibilities | Quality tools (if applicable) |
| April 07 – January 08 | Metadata standards | Checklist | All metadata successfully marked up in TEI P5 and mapped to DC | TS, C | TEI XML Schema |
| Progress All existing metadata from the Wilfred Owen Multimedia Digital archive has been converted from SGML to TEI P5. Once implemented within CONTENTdm this metadata can be exported to DC. The TEI has been converted and checked by the TEI specialists at Oxford University Computing Services and adheres to standards. |

| Output | Creation of machine-readable texts of poems. |
| --- | --- |
| Timing | Quality criteria | QA method(s) | Evidence of compliance | Quality responsibilities | Quality tools (if applicable) |
| July - December 07 | Metadata standards | Checklist | All text successfully marked up in TEI P5 and mapped to DC and displayed correctly. | TS | TEI XML Schema |
| Progress No progress has been made here yet. |

No changes to the plan are needed and objectives for the following reporting period remain the same:

- Implement the QA of audio into the digitisation workflow

- Implement the QA of video into the digitisation workflow

- Mark up and QA the TEI of full texts.

### 18. Dissemination Plan

Progress against plan for the reporting period

| Timing | Dissemination Activity | Audience | Purpose | Key Message |
| --- | --- | --- | --- | --- |
| March 07 | Press release | Institutional Community | Raise awareness | Information about project |
|  | Project Talk | Departmental Community | Raise awareness | Information about project |
|  | Newsletter | Institutional Community |  | Information about project |
|  | Flyer | JISC / Library Community |  | Information about project |
| Progress An article on the project appeared in Oxford’s Blueprint, LTG News, and Oxford Alumni Magazine A departmental talk was given on the project A flyer was created for dissemination |
| April 07 | Website | All interested parties | Raise awareness, keep interested parties informed of all development, encourage subject specialists to join user group | Information about project, call for participation |
|  | Project Blog | All interested parties | Keep interested parties informed of project progress | Project updates |
|  | Events Feed | All interested parties | Keep interested parties informed of up and coming events | Information about relevant events |
|  | News Feed | All interested parties | Keep interested parties informed of project news | Information about project news and related news items |
|  | WW1 Literature Discussion board | All interested parties | Raise awareness, encourage subject specialists to join user group | Information about project, call for participation, discussion of WW1 literature |
| Progress Project website set up at www.oucs.ox.ac.uk/ww1lit Project blog set up http://ww1lit.blogspot.com/ Events feed and news feed set up at http://www.oucs.ox.ac.uk/ww1lit/news/index.php Discussion boards set up at http://groups.google.com/group/ww1lit and http://groups.google.co.uk/group/modern-war-poetry/ , and a facebook group set up at http://oxford.facebook.com/group.php?gid=2566711287 |
| September 07 | Presentation | DRHA Conference | Raise awareness, collaboration | Information about project |
| Progress Presentation given at DRHA 2007 |

Other dissemination activities in the reporting period:

- The project has featured on the news pages of a number of other websites including the War Poets Association and Centre for First World War Studies at Birmingham University.

- Representation of the project at meetings of the Western Front Association

- Interviews with public figures (Ian Hislop and Max Arthur) released as podcasts on the project website

No changes to the plan are needed and objectives for the following reporting period remain the same:

- Teaching WW1 Literature workshop (November 2007)

- Creation of flyers and posters to raise awareness of the community collection

- Press release (March 2007) to raise awareness of the community collection

- Representation at Dead Reckoning. Passchendaele 1917 Conference: Beligium

The project team will be drawing up a dissemination plan specifically for the community collection in October 2007. This will then be integrated into the project dissemination plan.

### 19. Exit/Sustainability Plan

### Progress against plan for the reporting period

| Project Outputs | Action for Take-up & Embedding | Action for Exit |
| --- | --- | --- |
| Database |  | Ensure comprehensive technical documentation has been written to allow for maintenance and preservation. 5 year contract taken out on server maintenance. |
| Progress CONTENTdm provides comprehensive technical documentation. The software has been hosted on an institutional server with 10 years of server maintenance accounted for. |
| Digitised images of primary documents | Ensure that images are of a high quality and easily discoverable to promote use. Integration with tutorials | Ensure images have been captured to preservation standards. Ensure copyright and usage terms have been agreed to allow use after the end of the project. Images archived. |
| Progress Where possible all images have been captured to preservation standards of 800dpi, those that are captured at 600dpi are still of high enough quality for archival purposes. Copyright and usage terms have been secured under the JISC model licence Images are archived and backed-up on institutional hierarchical file server. |

No changes to the plan are needed and objectives for the following reporting period remain the same:

| Digitised audio | Ensure that audio files are of a high quality and easily discoverable to promote use. Integration with tutorials | Ensure audio has been captured to preservation standards. Ensure copyright and usage terms have been agreed to allow use after the end of the project. Audio archived. |
| --- | --- | --- |
| Digitised video | Ensure video files are of a high quality and easily discoverable to promote use. Integration with tutorials | Ensure video has been captured to preservation standards. Ensure copyright and usage terms have been agreed to allow use after the end of the project. Video archived. |
| Creation of machine readable texts of poems | Ensure all metadata conforms to current standards. Ensure easily discoverable to promote use. Integration with tutorials. | Ensure copyright and usage terms have been agreed to allow use after the end of the project. Metadata archived. |
| Creation of a web base interface to collect digitised items from the general public (community collection) | Ensure clear help pages and guidelines to facilitate easy use. Ensure that the site is usable and accessible. User group Dissemination activities. | The Community Collection Interface will only be available for 3 months however the tool will still be archived for possible future uses. Digitised items and metadata archived. |
| Metadata | Ensure all metadata conforms to current standards. | Ensure accurate documentation. Metadata archived |
| Creation of a web based user interface to allow searching, browsing, viewing, downloading of items | Ensure clear help pages and guidelines to facilitate easy use. Ensure that the site is usable and accessible. User group. Dissemination activities. | Ensure comprehensive technical documentation has been written to allow for maintenance and preservation. Ensure that the maintenance of the site is as automated as possible. Site archived. |
| Path creation tool to allow users to create personalised paths through the archive | Ensure clear help pages and guidelines to facilitate easy use. Ensure that the tool is usable and accessible. Example paths available. | Ensure comprehensive technical documentation has been written to allow for maintenance and preservation. Tool archived. |
| Seminars | Ensure tutorials are of a high quality and relevant to target audience. Ensure clear help pages and guidelines to facilitate easy use. User group. Dissemination activities. | Ensure copyright and usage terms have been agreed to allow use after the end of the project. |
| Documentation | Ensure that all documentation is available via the project website. | Ensure all documentation is available via the website. Documentation archived. |

| Project Outputs | Why Sustainable | Scenarios for Taking Forward | Issues to Address |
| --- | --- | --- | --- |
| Web-based interface | The website will be developed to ensure minimal maintenance after the project has been completed. The site will be hosted by Oxford University Computing Services | We have budgeted for 5 years of server maintenance after the end of the project. | Investigate further funding opportunities. |
| Community Collection | All items submitted to the community collection will be archived. | All items and metadata submitted to the collection will be stored on the Oxford Hierarchical File Server and available for further development. | Investigate further funding opportunities. Further research required to scope possibilities of the community collection. |

## Appendixes

### Appendix B. Workpackages

| WORKPACKAGES | Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1: Set up project | Apr 07 |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2: Identification of resources: stage 1 | Apr 07 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3: Digitisation: stage 1 | Apr 07 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4: Identification of resources: stage 2 | Sept 07 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5: Digitisation: stage 2 | Jan 08 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6: Setup content management platform | Aug 07 |  |  |  |  |  | 2 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7: Migration of existing metadata | Jun 07 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8: Creation of new metadata | May 07 |  |  |  |  |  |  |  |  |  | 4 |  |  |  |  |  |  | 5 |  |  |  |  |  |  |  |
| 9: Database population | Jul 07 |  |  |  |  |  |  | 6 |  | 7 | 8 |  |  |  |  |  |  | 9 |  |  |  |  |  |  |  |
| 10. Web interface development | Oct 07 |  |  |  |  |  |  |  |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  |  |  |  |
| 11. Development of Educational tools | Oct 07 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12. Dissemination | Apr 07 |  |  |  |  |  |  |  | 12 |  |  |  |  |  |  |  |  |  |  |  | 13 |  |  |  |  |
| 13. Project Admin | Apr 07 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Project start date: 1st April 2007

Project completion date: 31st March 2009

Duration: 24 months

| WORKPACKAGE 1: Project Initiation Objective: Establish project |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Recruitment | 01/01/07 | 27/02/07 | Staff recruited |  | SL, KL |
| Office Relocation | 26/03/07 | 31/03/07 | Establish project office |  | KL |
| Purchase Equipment | 01/03/07 | 31/04/07 | Equipment in place |  | KL, ML |
| Software Purchase | 01/03/07 | 31/04/07 | Software in place |  | KL, ML |
| Set up website | 01/04/07 | 31/03/07 | Set up of initial web pages |  | KL |
| Finalise work plan and budget | 01/04/07 | 31/05/07 | Detailed project plan | 1 | KL |
| Project start up meeting with Advisory Group | 01/04/07 | 31/04/07 | Advisory group meeting |  | SL, KL |
| 8. Contact all literary estates to confirm permission to use materials. | 01/01/07 | 31/03/07 | Receive confirmation from literary estates |  | SL, KL |
| WORKPACKAGE 2: Identification of items: stage 1 Objective: To select all items for digitisation that were identified in the initial project plan |  |  |  |  |  |
| Discuss and edit existing item lists with experts | 01/04/07 | 31/04/07 | Update item lists developed during the project proposal stage |  | KL |
| Visits to UK collections | 01/04/07 | 31/06/07 | Item lists |  | SL, KL, ES |
| Visits to US collections | 07/04/07 | 31/09/07 | Item lists |  | KL |
| Reconfirm item lists with experts | 01/05/07 | 31/09/07 |  |  | KL |
| WORKPACKAGE 3: Digitisation: stage 1 Objective: Digitisation of all items identified in the submitted project proposal |  |  |  |  |  |
| Digitisation of primary documents | 01/04/07 | 31/12/07 | Documents captured as TIFF images |  |  |
| Digitisation of contextual photographs | 01/06/07 | 31/12/07 | Photographs scanned from surrogates as JPEGS |  | ES |
| Digitization of contextual audio | 01/06/07 | 31/12/07 | Creation of MP3 files |  | ML |
| Digitization of contextual video | 01/06/07 | 31/12/07 | Creation of Quicktime files |  | ML |
| 16. Community collection | 01/02/07 | 31/06/08 | Selection of items submitted to be included in the archive |  | ES |
| WORKPACKAGE 4: Identification of items: stage 2 Objective: To select all additional items |  |  |  |  |  |
| Discuss and select additional items with experts | 01/09/07 | 31/12/07 | Update item lists developed during the project proposal stage |  | KL |
| Visits to collections | 01/09/07 | 31/01/07 | Item lists |  | SL, KL, ES |
| Reconfirm item lists with experts | 01/01/08 | 31/01/08 |  |  | KL |
| WORKPACKAGE 5: Digitisation: stage 2 Objective: To digitise additional items selected in workpackage 4 |  |  |  |  |  |
| Digitisation of primary documents | 01/01/08 | 31/04/08 | Documents captured as TIFF images |  |  |
| WORKPACKAGE 6: Setup content management platform Objective: ContentDM platform established |  |  |  |  |  |
| Test software against project requirements on providers server | 01/08/07 | 31/09/07 | Reports: Requirements mapping | 2 | ML |
| Install full version on project server | 15/09/07 | 31/09/07 | Prototype available |  | ML |
| 18. Setup full version with metadata fields, ready for upload of content | 31/09/07 | 15/10/07 | Database available | 3 | ML |
| WORKPACKAGE 7: Migration of existing metadata Objective: |  |  |  |  |  |
| Migration of existing metadata | 01/06/07 | 31/09/07 | Metadata migrated from SGML to TEI |  | ML |
| WORKPACKAGE 8: Creation of new metadata Objective: Create metadata for all digital objects |  |  |  |  |  |
| Creation of all metadata | 31/04/07 | 31/06/08 | Metadata available | 4 | ES |
| Community collection | 01/2/08 | 31/08/08 | Metadata available | 5 | ES |
| WORKPACKAGE 9: Population of database Objective: |  |  |  |  |  |
| Existing metadata | 01/07/07 | 31/10/07 | Existing metadata integrated | 6 | ML |
| Machine readable texts | 01/07/07 | 31/12/07 | Full texts integrated | 7 | ML |
| New metadata | 01/03/08 | 31/01/08 | New metadata integrated | 8 | ML |
| Community collection | 01/06/07 | 31/08/08 | Community collection integrated | 9 | ML |
| WORKPACKAGE 10: Web Interface development Objective: Develop usable and accessible web interface to archive database |  |  |  |  |  |
| Requirements gathering | 01/08/07 | 31/09/07 | Requirements set |  | KL |
| Community Collection submission interface | 01/10/07 | 31/02/08 | Community collection submission launched | 10 | C |
| Educational resources | 01/10/07 | 31/08/08 | Web interface to educational resources developed |  | C, ML |
| Federated search | 01/10/07 | 31/08/08 | Federated search developed |  | C, ML |
| Archive | 01/10/07 | 31/08/08 | Archive interface developed | 11 | C |
| WORKPACKAGE 11: Development of Educational Resources Objectives: Develop educational resources to support teaching and learning with archive resources |  |  |  |  |  |
| Integration of path creation tool | 01/10/07 | 31/09/08 | Path creation tool integrated |  | ML, WD |
| Content for new seminars | 01/01/08 | 31/07/08 | Content for new seminars written |  | TEA, KL, WD |
| WORKPACKAGE 12: Dissemination Objective: Disseminate and advertise project |  |  |  |  |  |
| Teaching WW1 Literature workshop | 12/11/07 | 12/11/07 | Workshop | 12 | SL |
| Community Collection | 01/01/08 | 01/06/08 | Press releases, conferences, posters, flyers |  | SL. KL |
| 35. Archive | 01/06/08 | 31/03/09 | Press releases, conferences, posters, flyers |  | SL, KL |
| Launch of archive | 11/11/08 | 11/11/08 | Final archive launched | 13 | KL, ML |
| WORKPACKAGE 13: Project Admin Objective: Administer project |  |  |  |  |  |
| Steering committee meetings | 01/04/07 | 31/03/09 | Steering group reports |  | KL |
| Biannual reports | 01/09/07 | 31/10/09 | Biannual reports |  | KL |
| Evaluation reports | 31/04/07 | 31/03/09 | Project blog, evaluation reports |  | KL |

Members of Project Team:

KL – Kate Lindsay

SL – Stuart Lee

ML -Michael Loizou

ES – Everett Sharp

C – Contractor

TEA – Teachers / Lecturers

Appendix C. Mapping Requirements to CONTENTdm

| Requirement | CONTENTdm Support |
| --- | --- |
| 1. Browsing |  |
| a. Sort by field type | Can sort up to 4 different field types |
| b. Sort by date | Supported by additional module that will be implemented |
| 2. Searching |  |
| a. Exact Phrase | Yes |
| b. All words | Yes |
| c. Non of words | Yes |
| d. Any of words | Yes |
| e. Across all fields | Yes |
| f. Across selected fields | Yes |
| g. By proximity | Yes |
| h. By date | Yes |
| i. By object type (image, audio, video, text) | Yes |
| 3. Allows integration of path creation scheme | Solution 1: Could use a modified version of CONTENTdm’s “favourites”. Solution 2: Develop the “path creation scheme” software to browse CONTENTdm. |
| 4. Full text search | Yes |
| 5. Integration of Community Collection | A bespoke collection and administrator interface will be developed for the community collection, metadata can be exported directly into CONTENTdm as the delivery system. |
| 6. Image zoom | Yes |
| 7. MP3 and M-PEG 4 support | Yes |
| 8. Metadata export | Tab-deliminated, Dublin Core, CONTENTdm standard XML, Custom XML |
| 9. Interoperability |  |
| a. Making our data discoverable | Free automated registration under the CONTENTdm for WorldCat. This will let people to discover items in our database when they follow links from results on popular Web search engines (like Google and Yahoo!), other worldcat partner sites or WorldCat.org. |
| b. Discovering other archive’s data | CONTENTdm does not provide a federated search interface to other archives but the project will use a federated search client to search other Z39.50 targets. |
| 10. Accessibility | Can customise CONTENTdm templates to conform to W3C standards. |

Appendix D.